## Slide 1
CIEL-OCL 2026
Midpoint Pulse Check
Where we stand · What's shipping · What needs alignment
May 7, 2026 · OCL Team Review
Week 13 of 26 · ~50%

## Slide 2
What We Set Out to Do
6-month SOW · February – July 2026
15%
CIEL Bridge
CIEL as bridge terminology to ICD-11, LOINC & others.
Multi-algorithm matching + AI assistant integration.
30%
CIEL Source Management
CIEL managed in CIEL Lab v2 + OCL TBv3.
Release pipeline, QA workflows, CIEL Admin retirement.
45%
CIEL + OpenMRS Implementers
TBv3 collection management, concept proposals.
Mapper team-based workflows & dictionary building.
10%
CIEL Content Curation
QA review of ~15k remaining CIEL concepts.
Naming, mappings, AI-assisted curation workflows.

## Slide 3
Milestone Tracker
Each milestone = a showcase demo that proves the capability is real and working
✅ Closed / Complete
🔄 Open — In Progress
❌ Overdue
⬜ Upcoming
[CIEL Bridge]
[CIEL Source Mgmt]
[CIEL Implementers]
[CIEL Content]
Feb 26 ✅
ICD11 Technical Demo
E2E Workflow (#41)
20/20 closed
Apr 2 🔴
ICD11 E2E
pre-pub dataset (#51)
0% · 0c/13o
May 7
ICD11 E2E
evaluation dataset (#59)
25% · 1c/3o
May 28
ICD11 E2E
country dataset (#55)
50% · 1c/1o
Jun 11
CIEL Bridge Showcase
all target repos (#57)
1 open
Mar 5 ✅
CIEL Lab v2 Concept
Manager — Filipe (#48)
5/5 closed
Mar 19 ✅
CIEL Lab v2 Mock
E2E — Andy (#49)
22/23 closed
Apr 2 🔴
CIEL Source Mgmt
QA Workflows (#53)
0% · 0c/5o
May 7
CIEL Release E2E
Filipe leads (#54)
Due today
Jun 11
Real-life CIEL Release
in CIEL Labs v2 (#56)
No issues yet
May 7
Collection & Ref
Creation E2E (#42)
53% · 14c/12o – Due today
May 15
Team-based Mapping &
Left Panel (#43)
Not yet scheduled
May 15
Collection Maintenance
+ CIEL Release (#44)
Not yet scheduled
May 29
Concept Proposals
E2E (#45)
0% · 0c/4o
Jun 26
Mapping Decision
Memory (#46)
0% · 0c/3o
Apr 9
CIEL Content E2E
Technical Showcase (#52)
0% · 0c/3o
Jun 25
Showcase Completed
CIEL Curation (#58)
No issues yet
Summary: ✅ 3 closed ❌ 3 overdue (Apr 2–9) 🔄 3 in progress ⬜ 8 upcoming

## Slide 4
# | Status | Bucket | Title | % | Due | Issues
41 | ✅ Closed | [CIEL Bridge] | ICD11 Technical Demo E2E Workflow | 100% | Feb 26 | 20/20
42 | 🔄 In Progress | [CIEL Implementers] | Collection & Reference Creation E2E | 53% | Apr 30 | 14c/12o
43 | ⬜ Upcoming | [CIEL Implementers] | Team-based Mapping & Left Panel E2E | ? | TBD | —
44 | ⬜ Upcoming | [CIEL Implementers] | Collection Maintenance E2E (+ CIEL Release) | ? | TBD | —
45 | ⬜ Upcoming | [CIEL Implementers] | Concept Proposals E2E Workflow | 0% | May 29 | 0c/4o
46 | ⬜ Upcoming | [CIEL Implementers] | Mapping Decision Memory Showcase | 0% | Jun 26 | 0c/3o
47 | ⬜ Upcoming | (Mapper) | Mapper Public Showcase — Wrap-up & Release Prep | ? | Jul | —
48 | ✅ Closed | [CIEL Source Mgmt] | CIEL Lab v2 Concept Manager — Filipe | 100% | Mar 5 | 5/5
49 | ✅ Closed | [CIEL Source Mgmt] | CIEL Lab v2 Mock E2E — Andy | 95% | Mar 19 | 22/23
51 | 🔴 Overdue | [CIEL Bridge] | ICD11 E2E on pre-publication dataset | 0% | Apr 2 | 0c/13o
52 | 🔴 Overdue | [CIEL Content] | Showcase CIEL Content E2E Technical Workflow | 0% | Apr 9 | 0c/3o
53 | 🔴 Overdue | [CIEL Source Mgmt] | CIEL Source Mgmt QA Workflows | 0% | Apr 2 | 0c/5o
54 | 🔄 In Progress | [CIEL Source Mgmt] | CIEL Release E2E Workflow — Filipe leads | ? | Apr 30 | ?
55 | 🔄 In Progress | [CIEL Bridge] | ICD11 E2E evaluation on country dataset | 50% | May 28 | 1c/1o
56 | ⬜ Upcoming | [CIEL Source Mgmt] | Real-life CIEL Release using CIEL Labs v2 | ? | Jun 11 | —
57 | ⬜ Upcoming | [CIEL Bridge] | CIEL Bridge Showcase (all target repos) | ? | Jun 11 | 1o
58 | ⬜ Upcoming | [CIEL Content] | Showcase Completed CIEL Content Curation | 0% | Jun 25 | —
59 | 🔄 In Progress | [CIEL Bridge] | ICD11 E2E on evaluation dataset | 25% | May 7 | 1c/3o
Note: #50 was closed/merged into #41 per the closed milestones list, so it's omitted. Cells marked ? couldn't be confirmed from the fetches — worth a quick check on #43, #44, #47, #54, #56, #57.
Cheat Sheet

## Slide 5
SOW Timeline by Project
Feb–Jul 2026 · Milestones = ◆ · filled = complete or in progress · ▲ = TODAY (Apr 29)
Feb
Mar
Apr
May
Jun
Jul
▲ TODAY
CIEL Bridge
(15%)
ICD-11 source & post-coord pipeline
Multi-algo matching (reranker, bridge)
ICD-11 automatch + LLM-terminologist
Evaluation + connectathon prep
Bridge showcase: ICD-11, LOINC, others
CIEL Source
Mgmt (30%)
CIEL Lab v2 Concept Manager
QA Workflows (validations, OpenMRS)
CIEL Release pipeline in CIEL Lab
Changelog + admin retirement plan
Full live release via CIEL Lab v2
#48
✅
#49
✅
#53
🔴
#54
#56
Implementers
(45%)
TBv3 Collections + References (Versions tab, Add Refs, Preview)
Mapper UX + Save to Collection
Concept Proposals (TBv3 + Mapper)
Team-based mapping workflows
Mapping decision memory
#45
#43
#44
#46
Content
Curation (10%)
QA pipeline + CIEL Lab work queue setup
~15k concept review (ongoing transversal)
AI QA tools (typo, spelling, AI assistant)
Showcase: completed curation
#52
🔴
#58
#55
🔄
#57
#41
✅
#51
🔴
#59
🔄
#42
🔄

## Slide 6
🔗 CIEL Bridge
15% of SOW · Milestones: 1 ✅ done, 1 🔄 in progress, 1 ❌ overdue, 2 upcoming
✅ COMPLETED
● ICD11 Technical Demo E2E — showcased Feb 12, closed 20/20 issues
● ICD-11 post-coordination microservice (normalize + AI naming)
● Custom bridge source generalized beyond CIEL (#2471)
● Configurable reranker + sentence-transformers v5.4 upgrade
● Enhanced Match Details panel (unified score, attributes)
● Validation dataset preparation underway
❌ OVERDUE (due Apr 2–16, ~0% complete)
● MS#51 — ICD11 E2E on pre-publication dataset (13 open issues)
→ Validation dataset, WHO automatch, LLM-terminologist, evaluation
● MS#59 — ICD11 E2E on evaluation dataset (3 open issues)
→ Requires more ticket definition plus some Mapper fixes
● MS#55 — Country dataset E2E — due May 28 (connectathon prep)
● MS#57 — CIEL Bridge full showcase — due Jun 11
⚠️ May ICD-11 Connectathon in Geneva is 3 weeks away.
→ Requires more ticket definition
● Geneva!
→ Milestone to be created - multiple overlapping initiatives
● Mapping architecture normalization underway

## Slide 7
🗄️ CIEL Source Management
30% of SOW · Milestones: 3 ✅ done, 1 ❌ overdue, 1 upcoming
✅ COMPLETED
● MS#48 — CIEL Lab v2 Concept Manager (Filipe) — 5/5 ✅ Mar 5
● MS#49 — CIEL Lab v2 Mock E2E (Andy) — 22/23 ✅ Mar 19
● CIEL releases continuing — v2026-04-28 just released ✅
● Concept Editor QA: names + mappings validation (#2405, #2408)
● OpenMRS FSN duplicate validation bug fixed (#2406)
● Export streaming crash fixed; API performance improvements
❌ OVERDUE — Behind Schedule
● MS#53 — CIEL Source Mgmt QA Workflows — 2/2
→ OpenMRS Validation Query, real-time schema, batch API
● MS#54 — CIEL Release E2E (Filipe) — 0%, due May 7 (5 open)
● CIEL Lab v2 Release pipeline (#2474) — in progress, complex
● Export formats analysis (#2475) + scripts (#2477, #2478) — open
● 🚨 Staging pollution (#2490, #2491) — release QA unreliable
● 🚨 CIEL Admin retirement plan — decision still pending
● 🚨 Gap: Identifying issues vs. acting upon them
● CIEL Lab used to push CIEL changes to Prod (mini win!)
⚠️ Need to bring together the QA/detection of issues and the bulk-editing based on QA

## Slide 8
🌐 CIEL + OpenMRS Implementers
45% of SOW - Requires more definition of requirements and designs for upcoming features!
TBv3 — TermBrowser
✅ Versions + Expansions tab live (M42) (#1983)
✅ Expansion CTAs: Create, Set Default, Delete, Rebuild
✅ Cascade component — reusable (#2440)
✅ Add Reference to Collection from outside (#2006)
✅ Reference Consumer + Detail view (#1854, #2432)
✅ Reference Preview CTA (#2007)
🔄 Add References within Collection (#2431)
🔄 API: Enhance references/preview/ endpoint (#2469)
🔄 Expansion selector on Concepts/Mappings (#2493)
⬜ Collection Maintenance
⬜ Concept Proposals MVP (#SOW-27) — not started
OCL Mapper
✅ Create project from existing (#2485)
✅ Dashboard row actions + kebab menu (#2486)
✅ API throttling overlay (#2483)
✅ Map project N+1 fix (5s → <1s) (#2479)
✅ Candidate pool persistence fixed (#2444)
✅ Multi-algo score details panel (#2315)
🔄 'Save to Collection' feature (#SOW-40)
🔄 UX improvements for CIEL Early Access users
🔄 Mapping decision memory (#SOW-21, 71)
⬜ Team-based mapping workflows (#SOW-2, 37, 39)
⬜ Large project support >1k rows (#SOW-32)
⚠️ Lots of progress made, but we need to prepare for community use. Need to open this up more to the community, not just the core team!
✅ Bridge is generic - can be done against any CIEL map source
✅ Multiple reranker models
🔄 Prompt template selection
✅ Request from community to contribute to OCL Mapper! Lots of interest!

## Slide 9
✏️ CIEL Content Curation
10% of SOW · Milestones: 0 ✅ closed, 1 ❌ overdue (partially done), 1 upcoming
✅ COMPLETED (features, not showcase)
● CIEL QA work queue: layout, filters, progress view (#2412)
● Casing triage migrated to CIEL Lab v2 (#2328) — ongoing
● Translation tools with LM pre-translation (FR/PT)
● Concept Editor QA validations (#2405, #2408)
● CIEL releases on schedule — v2026-04-28 released ✅
❌ OVERDUE + OPEN
● MS#52 — Showcase CIEL Content E2E Workflow — 0%, due Apr 2
→ 2 open issues – nearly ready to close?
● MS#58 — Showcase Completed Curation — due Jun 25
→ Goal: all ~15k concepts through QA
● ~15,000 concepts still need manual review — ongoing transversal task
● AI QA: typo + US/UK spelling detection tools (#2404)
● OCL AI Assistant reusable QA workflow (#SOW-57)
~15k concept QA progress:
~10–15%
CIEL content curation is a never-ending effort. Trying to reign this in as a team and do the most important stuff.
● New naming issues identified for translations

## Slide 10
Risks & Decisions Needed
Items requiring team attention or decision before the next iteration
🚨 HIGH
5 showcase milestones are overdue (Apr 2–16)
MS#51, #52, #53, #54, #59 all past due. Combined: 21 open issues + 2 showcases with zero issues linked. Need triage: reschedule, scope down, or reassign.
🚨 HIGH
Staging environment pollution (#2490, #2491)
Automated imports diverged staging from production. Duplicate retired mappings cause import crashes. CIEL release validation unreliable until fixed.
🚨 HIGH
ICD-11 hierarchy import bug (#2462) — connectathon in 4 weeks
parent_concept_urls lost after bulk import. Breaks bridge pipeline. Must resolve before May Geneva connectathon.
⚠️ MED
CIEL Admin retirement plan — decision pending (SOW Tracker #47)
No decision on Dropbox continuation or mysqldump script ownership. Blocks release pipeline milestone MS#54.
⚠️ MED
5 CIEL Implementer milestones are upcoming but behind
MS#42–46 cover Collection workflows, Team-based Mapping, Collection Maintenance, Concept Proposals, and Decision Memory. Need more support for building out requirements, designs, workflows, etc.

## Slide 11
Indirect Wins & Sneaky Goals
How we're making the most of limited time — and what we're learning along the way
🤖 AI-Powered Ticket Triage at Scale
Org-wide label taxonomy across 36 repos. 1,073 issues migrated. AI triage pipeline flags scope, risk & spec quality — cutting planning overhead.
📚 Spec-First Development with ocl-kb
KB-driven spec approach means developers move faster with less back-and-forth. Tickets link directly to KB specs — reducing PM time per ticket.
🎨 OCL Design System v1 Shipped
First public design system at openconceptlab.github.io/ocl-design-system. Speeds up TBv3 component decisions, reduces design review cycles.
🔬 AI-Assisted QA Workflows
LM-based typo detection, US/UK spelling tools, and AI pre-translation support in CIEL Lab. AI makes curation of 15k concepts tractable.
⚡ Performance Improvements Beyond SOW
N+1 query fix (5s→<1s mapper load), mapped-sources fix (38s→sub-second), ES indexing speedups. Users benefit immediately. (Shoutout Jon for lots of PRs!)
🏛️ Governance & Community Infrastructure
CONTRIBUTING.md, PR/release/ticket policies, 33-label taxonomy. Sets OCL up for sustainable community contribution beyond this project.

## Slide 12
What's Next — May through July
Priorities for the second half — organized around milestone delivery
Immediate (May)
Fix ICD-11 hierarchy bug + staging env (#2462, #2490)
Deliver MS#51: ICD11 E2E pre-pub dataset showcase
WHO ICD-11 automatch for Geneva connectathon
Agree on CIEL Admin retirement plan (unblocks MS#54)
Bulk Import Performance Improvements
Core Delivery (May–Jun)
MS#55: ICD11 E2E on country dataset (May 28)
CIEL Lab v2 release pipeline (#2474) → MS#56
Add References within Collection (#2431)
Concept Proposals MVP (#SOW-27)
Save to Collection (Mapper) (#SOW-40)
Stretch / Strategic (Jun–Jul)
MS#57: CIEL Bridge full showcase (Jun 11)
MS#58: Completed CIEL curation showcase (Jun 25)
Team-based Mapper workflows (scope to fit)
Mapper Public Showcase wrap-up — MS#47
Add mid-project Implementer showcase milestone
💬 Team: Do we reschedule the 5 overdue milestones, or formally descope them? Who owns each showcase?

## Slide 13
Good Progress. Busy Months Ahead.
3 milestones closed. 5 overdue and need triage.
13 weeks of execution left — let's align on the right priorities.
3
Milestones
closed ✅
5
Milestones
overdue ❌
13
Weeks
remaining
github.com/OpenConceptLab/ocl_issues/milestones