## Slide 1
CIEL-OCL 2026
Midpoint Pulse Check
Where we stand · What's shipping · What needs alignment
May 7, 2026 · OCL Team Review
Week 13 of 26 · ~50%

## Slide 2
What We Set Out to Do
6-month SOW · February – July 2026
15%
CIEL Bridge
CIEL as bridge terminology to ICD-11, LOINC & others.
Multi-algorithm matching + AI assistant integration.
30%
CIEL Source Management
CIEL managed in CIEL Lab v2 + OCL TBv3.
Release pipeline, QA workflows, CIEL Admin retirement.
45%
CIEL + OpenMRS Implementers
TBv3 collection management, concept proposals.
Mapper team-based workflows & dictionary building.
10%
CIEL Content Curation
QA review of ~15k remaining CIEL concepts.
Naming, mappings, AI-assisted curation workflows.

## Slide 3
Milestone Tracker
Each milestone = a showcase demo that proves the capability is real and working
✅ Closed / Complete
🔄 Open — In Progress
❌ Overdue
⬜ Upcoming
[CIEL Bridge]
[CIEL Source Mgmt]
[CIEL Implementers]
[CIEL Content]
Feb 26 ✅
ICD11 Technical Demo
E2E Workflow (#41)
20/20 closed
May 7
ICD11 E2E
pre-pub dataset (#51)
67% · 10c/5o
May 7
ICD11 E2E
evaluation dataset (#59)
33% · 2c/4o
May 28
ICD11 E2E
country dataset (#55)
50% · 1c/1o
Jun 11
CIEL Bridge Showcase
all target repos (#57)
No issues yet
Mar 5 ✅
CIEL Lab v2 Concept
Manager — Filipe (#48)
5/5 closed
Mar 19 ✅
CIEL Lab v2 Mock
E2E — Andy (#49)
22/23 closed
Apr 2 ✅
CIEL Source Mgmt
QA Workflows (#53)
2/2 closed
May 7
CIEL Release E2E
Filipe leads (#54)
0% · 0c/8o
Jun 11
Real-life CIEL Release
in CIEL Labs v2 (#56)
No issues yet
Apr 30
Collection & Ref
Creation E2E (#42)
67% · 20c/10o – Overdue
May 15
Team-based Mapping &
Left Panel (#43)
13% · 1c/7o
May 15
Collection Maintenance
+ CIEL Release (#44)
20% · 3c/12o
May 29
Concept Proposals
E2E (#45)
0% · 0c/4o
Jun 26
Mapping Decision
Memory (#46)
0% · 0c/3o
Apr 9 ✅
CIEL Content E2E
Technical Showcase (#52)
4/4 closed
Jun 25
Showcase Completed
CIEL Curation (#58)
No issues yet
Summary: ✅ 5 closed 🔄 7 in progress ⬜ 6 upcoming
May 18
Mini-event: Research
Presentation to DBMI (#60)
No issues yet

## Slide 4
# | Status | Bucket | Title | % | Due | Issues
41 | ✅ Closed | [CIEL Bridge] | ICD11 Technical Demo E2E Workflow | 100% | Feb 26 | 20/20
42 | 🔄 In Progress (Overdue) | [CIEL Implementers] | Collection & Reference Creation E2E | 67% | Apr 30 | 20c/10o
43 | 🔄 In Progress | [CIEL Implementers] | Team-based Mapping & Left Panel E2E | 13% | May 15 | 1c/7o
44 | 🔄 In Progress | [CIEL Implementers] | Collection Maintenance E2E (+ CIEL Release) | 20% | May 15 | 3c/12o
45 | ⬜ Upcoming | [CIEL Implementers] | Concept Proposals E2E Workflow | 0% | May 29 | 0c/4o
46 | ⬜ Upcoming | [CIEL Implementers] | Mapping Decision Memory Showcase | 0% | Jun 26 | 0c/3o
47 | ⬜ Upcoming | (Mapper) | Mapper Public Showcase — Wrap-up & Release Prep | 0% | Jul 8 | 0c/5o
48 | ✅ Closed | [CIEL Source Mgmt] | CIEL Lab v2 Concept Manager — Filipe | 100% | Mar 5 | 5/5
49 | ✅ Closed | [CIEL Source Mgmt] | CIEL Lab v2 Mock E2E — Andy | 95% | Mar 19 | 22/23
51 | 🔄 In Progress | [CIEL Bridge] | ICD11 E2E on pre-publication dataset | 67% | May 7 | 10c/5o
52 | ✅ Closed | [CIEL Content] | Showcase CIEL Content E2E Technical Workflow | 100% | Apr 9 | 4c/0o
53 | ✅ Closed | [CIEL Source Mgmt] | CIEL Source Mgmt QA Workflows | 100% | Apr 2 | 2c/0o
54 | 🔴 Overdue | [CIEL Source Mgmt] | CIEL Release E2E Workflow — Filipe leads | 0% | Apr 30 | 0c/8o
55 | 🔄 In Progress | [CIEL Bridge] | ICD11 E2E evaluation on country dataset | 50% | May 28 | 1c/1o
56 | ⬜ Upcoming | [CIEL Source Mgmt] | Real-life CIEL Release using CIEL Labs v2 | ? | Jun 11 | —
57 | ⬜ Upcoming | [CIEL Bridge] | CIEL Bridge Showcase (all target repos) | ? | Jun 11 | 0c/0o
58 | ⬜ Upcoming | [CIEL Content] | Showcase Completed CIEL Content Curation | 0% | Jun 25 | —
59 | 🔄 In Progress | [CIEL Bridge] | ICD11 E2E on evaluation dataset | 33% | May 7 | 2c/4o
60 | ⬜ Upcoming | [CIEL Bridge] | Mini-event: Research Presentation to DBMI | — | May 18 | 0c/0o
Note: #50 was closed/merged into #41 per the closed milestones list, so it’s omitted. Data refreshed from GitHub API, May 7, 2026. All ? values resolved.
Cheat Sheet

## Slide 5
SOW Timeline by Project
Feb–Jul 2026 · Milestones = ◆ · filled = complete or in progress · ▲ = TODAY (May 7)
Feb
Mar
Apr
May
Jun
Jul
▲ TODAY
CIEL Bridge
(15%)
ICD-11 source & post-coord pipeline
Multi-algo matching (reranker, bridge)
ICD-11 automatch + LLM-terminologist
Evaluation + connectathon prep
Bridge showcase: ICD-11, LOINC, others
CIEL Source
Mgmt (30%)
CIEL Lab v2 Concept Manager
QA Workflows (validations, OpenMRS)
CIEL Release pipeline in CIEL Lab
Changelog + admin retirement plan
Full live release via CIEL Lab v2
#48
✅
#49
✅
#53✅
#54
#56
Implementers
(45%)
TBv3 Collections + References (Versions tab, Add Refs, Preview)
Mapper UX + Save to Collection
Concept Proposals (TBv3 + Mapper)
Team-based mapping workflows
Mapping decision memory
#45
#43
#44
#46
Content
Curation (10%)
QA pipeline + CIEL Lab work queue setup
~15k concept review (ongoing transversal)
AI QA tools (typo, spelling, AI assistant)
Showcase: completed curation
#52✅
#58
#55
🔄
#57
#41
✅
#51
#59
🔄
#42
🔄
#60

## Slide 6
🔗 CIEL Bridge
15% of SOW · Milestones: 1 ✅ done, 1 🔄 in progress, 1 ❌ overdue, 2 upcoming
✅ COMPLETED
● ICD11 Technical Demo E2E — showcased Feb 12, closed 20/20 issues
● ICD-11 post-coordination microservice (normalize + AI naming)
● Custom bridge source generalized beyond CIEL (#2471)
● Configurable reranker + sentence-transformers v5.4 upgrade
● Enhanced Match Details panel (unified score, attributes)
● Validation dataset preparation underway
❌ OVERDUE (due Apr 2–16, ~0% complete)
● MS#51 — ICD11 E2E on pre-publication dataset (67% · 10c/5o)
→ Mapper info model refactor PR in review (Sunny) — nearly done
● MS#59 — ICD11 E2E on evaluation dataset (33% · 2c/4o)
→ Requires more ticket definition plus some Mapper fixes
● MS#55 — Country dataset E2E — due May 28 (connectathon prep)
● MS#57 — CIEL Bridge full showcase — due Jun 11
⚠️ ICD-11 Connectathon in Geneva is ~3 weeks away (week of May 28). New milestone to be created.
→ Requires more ticket definition
● Geneva!
→ Milestone pending – will contain multiple overlapping initiatives
● Mapping architecture normalization underway
● Multiple reranker models now configurable
● Prompt template selection (PR almost merged)

## Slide 7
🗄️ CIEL Source Management
30% of SOW · Milestones: 3 ✅ done, 1 ❌ overdue, 1 upcoming
✅ COMPLETED
● MS#48 — CIEL Lab v2 Concept Manager (Filipe) — 5/5 ✅ Mar 5
● MS#49 — CIEL Lab v2 Mock E2E (Andy) — 22/23 ✅ Mar 19
● CIEL releases continuing — v2026-04-28 just released ✅
● Concept Editor QA: names + mappings validation (#2405, #2408)
● OpenMRS FSN duplicate validation bug fixed (#2406)
● Export streaming crash fixed; API performance improvements
❌ OVERDUE — Behind Schedule
● MS#53 — CIEL Source Mgmt QA Workflows — 2/2
→ OpenMRS Validation Query, real-time schema, batch API
● MS#54 — CIEL Release E2E (Filipe) — 0% · 0c/8o · Overdue (Apr 30)
● CIEL Lab v2 Release pipeline (#2474) — in progress, complex
● Export formats analysis (#2475) + scripts (#2477, #2478) — open
● 🚨 Staging pollution (#2490, #2491) — release QA unreliable
● 🚨 CIEL Admin retirement plan — decision still pending
● CIEL Lab was used to push CIEL changes to Prod (mini win!)
⚠️ Need to bring together the QA/detection of issues and the bulk-editing based on QA
● Bulk import pre-sort performance fix — Filipe PR in progress

## Slide 8
🌐 CIEL + OpenMRS Implementers
45% of SOW - Requires more definition of requirements and designs for upcoming features!
TBv3 — TermBrowser
✅ Versions + Expansions tab live (M42) (#1983)
✅ Expansion CTAs: Create, Set Default, Delete, Rebuild
✅ Cascade component — reusable (#2440)
✅ Add Reference to Collection from outside (#2006)
✅ Reference Consumer + Detail view (#1854, #2432)
✅ Reference Preview CTA (#2007)
🔄 Add References within Collection (#2431)
🔄 API: Enhance references/preview/ endpoint (#2469)
🔄 Expansion selector on Concepts/Mappings (#2493)
⬜ Collection Maintenance MVP – Incepted but not fully documented
⬜ Concept Proposals MVP — not started
OCL Mapper
✅ Create project from existing (#2485)
✅ Dashboard row actions + kebab menu (#2486)
✅ API throttling overlay (#2483)
✅ Map project N+1 fix (5s → <1s) (#2479)
✅ Candidate pool persistence fixed (#2444)
✅ Multi-algo score details panel (#2315)
🔄 'Save to Collection' feature
🔄 UX improvements for CIEL Early Access users
🔄 Mapping decision memory
⬜ Team-based mapping workflows
⬜ Large project support >1k rows
⚠️ Lots of progress made, but we need to prepare for community use. Access/cost model needed before broader rollout — community contributor interest already received.
✅ Bridge generic — runs against any mapped source (not just CIEL)
✅ Multiple re-ranker models configurable
🔄 Prompt template selection (PR almost merged)

## Slide 9
✏️ CIEL Content Curation
10% of SOW · Milestones: 1 ✅ closed, 0 ❌ overdue, 1 upcoming
✅ COMPLETED (features, not showcase)
● CIEL QA work queue: layout, filters, progress view (#2412)
● Casing triage migrated to CIEL Lab v2 (#2328) — ongoing
● Translation tools with LM pre-translation (FR/PT)
● Concept Editor QA validations (#2405, #2408)
● CIEL releases on schedule — v2026-04-28 released ✅
⏳ OPEN + UPCOMING
● MS#58 — Showcase Completed Curation — due Jun 25
→ Goal: all ~15k concepts through QA
● ~15,000 concepts still need manual review — ongoing transversal task
● AI QA: typo + US/UK spelling detection tools (#2404)
● OCL AI Assistant reusable QA workflow
~15k concept QA progress:
~10–15%
CIEL content curation is a never-ending effort. Trying to reign this in as a team and do the most important stuff.
● New naming issues identified for translations
● MS#52 — Showcase CIEL Content E2E Workflow — ✅ CLOSED (4/4 issues)

## Slide 10
Risks & Decisions Needed
Items requiring team attention or decision before the next iteration
🚨 HIGH
Staging environment is unreliable — automated imports have diverged it from production
Duplicate retired mappings are causing import crashes, making it impossible to confidently validate CIEL releases in staging. Any milestone that requires a tested release is blocked until this is resolved.
🚨 HIGH
ICD-11 bridge pipeline is broken — connectathon in Geneva is three weeks away
Bulk imports are silently dropping parent concept relationships, which breaks the ICD-11 bridge pipeline end-to-end. This must be resolved before the May Geneva connectathon or the showcase will not be viable.
⚠️ MED
CIEL Admin tool has no owner and no retirement plan — quietly blocking a key milestone
There is still no decision on whether to continue using Dropbox-based exports or migrate to a scripted process. Until ownership is established, the CIEL Release pipeline milestone cannot close.
⚠️ MED
Several upcoming Implementer milestones are under-defined and at risk of slipping
The milestones covering team-based mapping, collection maintenance, and concept proposals lack finalized requirements and designs. Two have now started and two are due mid-May — the team needs more bandwidth to shape this work before the deadlines arrive.

## Slide 11
Indirect Wins & Sneaky Goals
How we're making the most of limited time — and what we're learning along the way
🤖 AI-Powered Ticket Triage at Scale
Org-wide label taxonomy across 36 repos. 1,073 issues migrated. AI triage pipeline flags scope, risk & spec quality — cutting planning overhead.
📚 Spec-First Development with ocl-kb
KB-driven spec approach means developers move faster with less back-and-forth. Tickets link directly to KB specs — reducing PM time per ticket.
🎨 OCL Design System v1 Shipped
First public design system at openconceptlab.github.io/ocl-design-system. Speeds up TBv3 component decisions, reduces design review cycles.
🔬 AI-Assisted QA Workflows
LM-based typo detection, US/UK spelling tools, and AI pre-translation support in CIEL Lab. AI makes curation of 15k concepts tractable.
⚡ Performance Improvements Beyond SOW
N+1 query fix (5s→<1s mapper load), mapped-sources fix (38s→sub-second), ES indexing speedups. Users benefit immediately. (Shoutout Jon for lots of PRs!)
🏛️ Governance & Community Infrastructure
CONTRIBUTING.md, PR/release/ticket policies, 33-label taxonomy. Sets OCL up for sustainable community contribution beyond this project.

## Slide 12
What's Next — May through July
Priorities for the second half — organized around milestone delivery
Immediate (May)
Core Delivery (May–Jun)
Stretch / Strategic (Jun–Jul)
Fix ICD-11 hierarchy bug + staging env (#2462, #2490)
DBMI research presentation prep (MS#60 · May 18)
Deliver MS#51: ICD11 E2E pre-pub dataset showcase
WHO ICD-11 automatch for Geneva connectathon (May 25)
Agree on CIEL Admin retirement plan (unblocks MS#54)
Bulk Import Performance Improvements
Merge mapper information model refactor (Sunny review → May 8)
MS#55: ICD11 E2E on country dataset (May 28)
CIEL Lab v2 release pipeline (#2474) → MS#56
Add References within Collection (#2431)
Concept Proposals MVP
Save to Collection (Mapper)
MS#43: Team-based Mapping & Left Panel (May 15)
MS#44: Collection Maintenance E2E
(May 15)
MS#57: CIEL Bridge full showcase (Jun 11)
MS#58: Completed CIEL curation showcase (Jun 25)
Team-based Mapper workflows (scope to fit)
Mapper Public Showcase wrap-up — MS#47

## Slide 13
Good Progress. Busy Months Ahead.
5 milestones closed. 1 overdue. 2 due today.
13 weeks of execution left — let's align on the right priorities.
5
Milestones
closed ✅
1
Milestone
overdue ❌
13
Weeks
remaining
github.com/OpenConceptLab/ocl_issues/milestones